## Project_Work_Flow
Outline Level | Name | Start | Finish | Duration | % Complete
1 | Automated Asset Oversight and Maintenance Enhancement (AATOME) | 2024-02-01 | 2025-11-07 | 462 day | 0
2 | Project Initiation | 2024-02-01 | 2024-02-07 | 5 day | 0
3 | Define Project Objectives and Scope | 2024-02-01 | 2024-02-05 | 3 day | 0
3 | Project Kickoff Meeting | 2024-02-05 | 2024-02-07 | 3 day | 0
3 | Meeting Team | 2024-02-05 | 2024-02-07 | 3 day | 0
2 | Preliminary Research | 2024-02-08 | 2024-04-12 | 47 day | 0
3 | Literature Review | 2024-02-08 | 2024-02-27 | 14 day | 0
3 | Market Research | 2024-02-21 | 2024-03-11 | 14 day | 0
3 | Feasibility Study | 2024-03-12 | 2024-03-29 | 14 day | 0
3 | Review and Summarise | 2024-04-01 | 2024-04-12 | 10 day | 0
2 | Data Collection and Preprocessing | 2024-04-15 | 2024-07-05 | 60 day | 0
3 | Define Image Collection Protocol | 2024-04-15 | 2024-04-26 | 10 day | 0
3 | Image Collection | 2024-04-29 | 2024-05-17 | 15 day | 0
3 | Image Labelling | 2024-05-20 | 2024-06-14 | 20 day | 0
3 | Image Preprocessing and Quality Enhancement | 2024-06-17 | 2024-07-05 | 15 day | 0
2 | Model Development and Training | 2024-07-08 | 2024-10-25 | 80 day | 0
3 | Choose and Implement Preprocessing Methods | 2024-07-08 | 2024-08-02 | 20 day | 0
3 | Model Design and Train | 2024-08-02 | 2024-09-12 | 30 day | 0
3 | Model Optimization and Hyperparameter Tuning | 2024-09-06 | 2024-10-17 | 30 day | 0
3 | Validate Model Performance | 2024-08-16 | 2024-10-25 | 51 day | 0
2 | Unsupervised Anomaly Detection Integration | 2024-10-28 | 2025-01-17 | 60 day | 0
3 | Integrate Unsupervised Learning Techniques | 2024-10-28 | 2025-01-10 | 55 day | 0
3 | Test and Validate Anomaly Detection | 2024-11-15 | 2025-01-17 | 46 day | 0
2 | System Integration and Testing | 2025-01-20 | 2025-05-30 | 95 day | 0
3 | Develop Integration Plan | 2025-01-20 | 2025-01-31 | 10 day | 0
3 | User Interface Design | 2025-02-03 | 2025-03-21 | 35 day | 0
4 | Design UI for Inspection Results | 2025-02-03 | 2025-02-14 | 10 day | 0
4 | Review and Refine UI Design | 2025-02-17 | 2025-02-28 | 10 day | 0
4 | Create UI | 2025-02-24 | 2025-03-21 | 20 day | 0
3 | Integrate Trained Models with Existing System | 2025-03-24 | 2025-04-04 | 10 day | 0
3 | Conduct Unit Testing | 2025-04-07 | 2025-04-18 | 10 day | 0
3 | Conduct Integration Testing | 2025-04-21 | 2025-05-02 | 10 day | 0
3 | Conduct End-to-End Testing | 2025-05-05 | 2025-05-16 | 10 day | 0
3 | Conduct Performance Testing | 2025-05-19 | 2025-05-30 | 10 day | 0
2 | Deployment and Monitoring | 2025-06-02 | 2025-07-25 | 40 day | 0
3 | Deploy Integrated System | 2025-06-02 | 2025-06-27 | 20 day | 0
3 | Monitor System Performance | 2025-06-30 | 2025-07-25 | 20 day | 0
2 | Revision/Revisit | 2025-07-28 | 2025-09-05 | 30 day | 0
2 | Final Documentation and Reporting | 2024-02-01 | 2025-10-24 | 452 day | 0
3 | Prepare Project Documentation | 2024-02-01 | 2025-09-26 | 432 day | 0
3 | Create Final Project Report | 2025-09-29 | 2025-10-24 | 20 day | 0
2 | Project Closure | 2025-10-27 | 2025-11-07 | 10 day | 0
3 | Conduct Project Review and Evaluation | 2025-10-27 | 2025-11-07 | 10 day | 0